Sample training prOgram checklist

TRAINING: 	DATE: 	LOCATION:

| TASK | PERSON(S) RESPONSIBLE | TASK BEGINS | DATE DUE | DATE DONE |
| --- | --- | --- | --- | --- |
| PRE-COURSE PREPARATION |  |
| MARKETING |  |
| Ensure proper paper is stocked in photocopy room; order more when necessary |  |  |  |  |
| Produce a draft of the flyer for this course |  |  |  |  |
| Obtain marketing/mailing list from ALA |  | 6 months |  |  |
| Photocopy, fold, label, and stamp brochures for mailing |  | 6 months |  |  |
| FACULTY |  |
| Invite faculty (initial contact) |  | 6-7 months |  |  |
| Draft 1st faculty confirmation letters |  | 6 months |  |  |
| Produce A/V fax-back form |  | 6 months |  |  |
| Mail 1st faculty confirmation letters with the draft agenda, draft objectives, previous outline(s), and A/V fax-back form |  | 5-6 months |  |  |
| Fax 2nd faculty letters with their final outlines, agenda, objectives, and directions to the conference center |  | 1+ weeks |  |  |
| REGISTRATION – PARTICIPANTS |  |
| Enter participants into database |  | As needed |  |  |
| Draft participant confirmation letters |  | 4-5 months |  |  |
| Send confirmation letters with directions to the conference center |  | As needed |  |  |
| Create name tags for participants, faculty and staff |  | 5 days |  |  |
| Create sign-in sheets for registration |  | 1 week |  |  |
| SYLLABUS |  |
| Create file folders for course materials |  | 6 months |  |  |
| Develop draft agenda and objectives |  | 6 months |  |  |
| Place work order (perfect bound books), after approval of quote |  | 3 months |  |  |
| Finalize agenda |  | 5 weeks |  |  |

Distribution:

| <<list names>> |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |

These individuals are proofers.  Please allow at least one (1) day per person for proofing

| TASK | PERSON(S) RESPONSIBLE | TASK BEGINS | DATE DUE | DATE DONE |
| --- | --- | --- | --- | --- |
| SYLLABUS (continued) |  |
| Gather clean copies of reprints and outlines readily available |  | 6 weeks |  |  |
| Draft book cover for review, then finalize |  | 3 months |  |  |
| Outlines, new reprints (also A/V and travel forms), slide files via email due at Training Center |  | 6 weeks |  |  |
| Contact faculty and give drop-dead due date for changes |  | 5+ weeks |  |  |
| Word process syllabus (include cover page, Faculty List) |  | 4+ weeks |  |  |
| Review syllabus content and edit |  | 4 weeks |  |  |
| Handouts due at Training Center |  | 4 weeks |  |  |
| Submit syllabus materials and pagination for printing |  | 3+ weeks |  |  |
| 1st proof returned (with original materials) to Training Center |  | 3 weeks |  |  |
| Review syllabus proof and edit |  | 2+ weeks |  |  |
| Resubmit revised and additional materials with proof for printing |  | 2 weeks |  |  |
| 2nd proof to Training Center |  | 1+ weeks |  |  |
| Review and edit 2nd proof (if necessary) |  | 1+ weeks |  |  |
| Return revised and additional materials for final printing |  | 1+ weeks |  |  |
| Complete syllabi to be delivered to training site |  | 2 days |  |  |
| SLIDES/VISUAL PRESENTATIONS |  |
| Review slide content & colors. Format for prints, if necessary. |  | 2+ weeks |  |  |
| All slides/PowerPoint presentations developed and ready to present |  | 2 weeks |  |  |
| PORTFOLIO |  |
| Check stock of brochures; order more if necessary |  | 2-3 months |  |  |
| Produce evaluation forms, credit page, and pre- & post-tests |  | 2 months |  |  |
| Copy materials & assemble portfolios |  | 2 weeks |  |  |
| LOGISTICS |  |
| Finalize contract with training site; provide a copy to TA |  | 4-5 months |  |  |
| Determine needs from A/V fax-back forms |  | 4 months |  |  |
| Arrange A/V needs with training site |  | 4 months |  |  |
| Order catering |  | 4-5 months |  |  |
| Create signs (course name, registration, help desk, etc.) |  | 3 weeks |  |  |

| TASK | PERSON(S) RESPONSIBLE | TASK BEGINS | DATE DUE | DATE DONE |
| --- | --- | --- | --- | --- |
| LOGISTICS (continued) |  |
| Call to confirm room arrangements, A/V, catering, outside signs, and all other logistics |  | 2 days |  |  |
| Assemble materials to be delivered to site (handouts, portfolios, name tags, registration sheets, signs, packing tape, laser pointers, signs, easels, etc.) to ship with FedEx? |  | 2 weeks |  |  |
| STAFFING |  |
| Assign task to each staff and create staffing instruction (if applicable) |  | 1 week |  |  |
| POST-COURSE TASKS |
| EVALUATION TOOLS |  |
| Summarize evaluations, worksheets, and questionnaires. |  | 2 days after |  |  |
| Update participants’ course status & credit in database |  | 2+ week after |  |  |
| Create and send CEU certificates/certificates of participation |  | 4 weeks after |  |  |
| Prepare evaluation pages for individual faculty |  | 4 weeks after |  |  |
| Develop and mail out faculty thank-you letters with evaluation summary |  | 5 weeks after |  |  |
| Route copy of evaluation summaries among the training team |  | 5 weeks after |  |  |
| FOLLOW-UP |  |
| F/U travel reimbursement with faculty and purchasing (if applicable) |  | 3 weeks after |  |  |
| Disassemble syllabus originals |  | 3 weeks after |  |  |
| File all documentation in course files |  | 3 weeks after |  |  |
| Update CNTC training file list of new CVs, reprints, and outlines |  | 3 weeks after |  |  |