<<Place your agency/clinic identifying information here>>

Latent TB Infection Program — Action Plan

List Team Members: (Name, Title)

	
STEP
	ACTIVITY / DESCRIPTION


	
RESPONSIBLE PERSON
	DUE DATE
	DATE COMPLETE

	


	STEP 1
	SITUATIONAL ANALYSIS

	1-A
	Identify high-risk groups for LTBI and TB disease within your jurisdiction.
	
	
	

	1-B
	Develop a community profile that describes your target groups in detail.
	
	
	

	1-C
	Assess your organization’s existing capacity and resources for implementing an LTBI program.
	
	
	

	

	STEP 2
	GUIDELINES, PROTOCOLS, AND STRATEGIES

	2-A
	Review guidelines by ATS and CDC, as well as the MMWR, for targeted testing and treatment of LTBI.
	
	
	

	2-B
	Review your local LTBI treatment protocol or establish one if it is not currently in place.   
	
	
	

	2-C
	Determine the approaches most applicable to your community and situation by studying this Toolbox and other sources.
	
	
	

	

	STEP 3
	PROGRAM FRAMEWORK

	3-A
	Determine and invite members who will be involved in the development of the program framework.
	
	
	

	3-B
	Set up a process for considering questions and issues, making decisions, and achieving consensus.
	
	
	

	3-C
	Develop the framework for your LTBI program.
	
	
	

	3-D
	Document and distribute the agreed-upon program framework and key elements.
	
	
	


	STEP
	
ACTIVITY / DESCRIPTION


	RESPONSIBLE PERSON
	DUE DATE
	DATE COMPLETE

	


	STEP 4
	BUDGET AND FUNDING

	4-A
	Develop a preliminary financial plan and budget.
	
	
	

	4-B
	Develop a list of prospective sources for funding and obtain information on their application requirements and procedures.
	
	
	

	4-C
	Develop and submit funding proposals.
	
	
	

	4-D
	Set up financial management systems to monitor income and expenditures.
	
	
	

	

	STEP 5
	ACTION PLAN

	5-A
	Assign a staff person to be in charge of the implementation process.
	
	
	

	5-B
	Design or adopt a checklist or action plan outline to use as a planning tool.
	
	
	

	5-C
	Distribute the action plan to everyone who is responsible for the activities/tasks and to other stakeholders.
	
	
	

	5-D
	Review and update the action plan regularly.
	
	
	

	


	STEP 6
	COMMUNITY PARTNERS

	6-A
	Assess your needs and expectations of what the community partners and organizations can offer.
	
	
	

	6-B
	Identify prospective partners and the potential benefits and drawbacks of collaborating with each one.
	
	
	

	6-C
	Contact prospective partners.
	
	
	

	6-D
	Discuss and agree upon the scope of services, cost allocation, roles and responsibilities, and evaluation standards.
	
	
	

	6-E
	Negotiate and execute an MOU.
	
	
	

	


	STEP 7
	COMMUNITY OUTREACH

	7-A
	Research effective outreach strategies.
	
	
	

	7-B
	Explore ways to collaborate with community partners on your outreach efforts.
	
	
	

	7-C
	Develop an outreach action plan.
	
	
	


	STEP
	
ACTIVITY / DESCRIPTION


	RESPONSIBLE PERSON
	DUE DATE
	DATE COMPLETE

	

	STEP 8
	CULTURALLY APPROPRIATE CARE

	8-A
	Identify your internal resources for communicating and working with members of the cultural, ethnic, and linguistic groups.
	
	
	

	8-B
	Identify external resources.
	
	
	

	8-C
	Arrange with the identified resources to obtain services and acquire materials.
	
	
	

	


	STEP 9
	INCENTIVES AND ENABLERS

	9-A
	Research possible incentives and enablers for your target groups.
	
	
	

	9-B
	Decide on an initial menu of incentives and enablers. Modify list as new patient needs are identified.
	
	
	

	9-C
	Identify sources for the selected incentives and enablers and make the arrangements to have them available for distribution.
	
	
	

	9-D
	Establish guidelines and procedures for distribution.
	
	
	

	9-E
	Set up referral mechanisms to link patients with programs, goods, or services that your program cannot provide.
	
	
	

	9-F
	Plan for regular evaluation of incentives and enablers for their effectiveness and problems.
	
	
	

	


	STEP 10
	LOCATION

	10-A
	Decide where your services should be located.
	
	
	

	10-B
	Determine your space needs and how you will reconcile them with your budget.
	
	
	

	10-C
	Decide on the space option that makes the most sense for your program.
	
	
	

	10-D
	Establish the terms and conditions of your use of the selected space.
	
	
	

	10-E
	Design a site plan.
	
	
	

	10-F
	Determine the kinds of furnishings and equipment needed and develop an acquisition plan.
	
	
	

	10-G
	Engage suppliers to accomplish needs to make the space suitable for your program’s use.
	
	
	

	10-H
	Arrange your move into the space.
	
	
	


	STEP
	
ACTIVITY / DESCRIPTION


	RESPONSIBLE PERSON
	DUE DATE
	DATE COMPLETE

	

	STEP 11
	ADMINISTRATIVE PROTOCOLS

	11-A
	Review available models for LTBI treatment program administrative procedures.
	
	
	

	11-B
	Determine what modifications are needed to fit your program’s situation and locality.
	
	
	

	11-C
	Develop and document specific protocols that your program will use.
	
	
	

	11-D
	Distribute the protocols to staff members.
	
	
	

	
	
	
	
	

	STEP 12
	CLINICAL PROTOCOLS 

	12-A
	Review available models for clinical procedures.
	
	
	

	12-B
	Determine the needs to adapt the models to your program’s situation and locality.
	
	
	

	12-C
	Develop and document the specific protocols that your program will use.
	
	
	

	12-D
	Distribute the completed protocols to staff members and provide training, as necessary.
	
	
	

	

	STEP 13
	STAFFING REQUIREMENTS

	13-A
	Assess the staffing requirements of your program.
	
	
	

	13-B
	Develop or modify job descriptions to incorporate program responsibilities.
	
	
	

	13-C
	Determine what resources will be required for the staff.
	
	
	

	13-D
	Develop and implement a recruitment action plan and timeline.
	
	
	

	

	STEP 14
	TRAINING

	14-A
	Identify the training needs.
	
	
	

	14-B
	Create an action plan for conducting training.
	
	
	

	14-C
	Set up a schedule and handle logistical arrangements for conducting training sessions.
	
	
	

	14-D
	Conduct the training program.
	
	
	

	

	STEP 15
	EVALUATION
	
	
	

	15-A
	Determine measures, standards, and outcomes to evaluate your program.
	
	
	

	15-B
	Develop and document procedures for conducting the evaluation and collecting, analyzing, and reporting the data.
	
	
	

	15-C
	Set up a schedule for regular program evaluations.
	
	
	

	15-D
	Conduct the scheduled evaluations and assess the results.
	
	
	


PAGE  

LTBI Program Action Plan
Page 4 of 4


